## JIRA_Backlog
Issue ID | Epic | User Story | Story Points | Assignee | Branch Name | Status
HGV-1 | Setup | Setup Flask project structure | 3 | Adarsh Singh | feature/project-setup | Done
HGV-2 | Setup | Install and configure MediaPipe | 3 | Mihir Gupta | feature/mediapipe-setup | Done
HGV-3 | Setup | Integrate OpenCV | 5 | Shivam Dhar Dubey | feature/opencv-integration | In Progress
HGV-4 | Setup | Configure virtual environment | 2 | Siya Gangwar | chore/env-setup | Done
HGV-5 | Webcam | Webcam access | 5 | Janhsi Gupta | feature/webcam-access | Done
HGV-6 | Webcam | Flask video streaming | 8 | Gaurav Patel | feature/video-stream | In Progress
HGV-7 | Webcam | Camera error handling | 5 | Danish Khan | feature/camera-error-handling | To Do
HGV-8 | Detection | Hand detection | 8 | Mihir Gupta | feature/hand-detection | Done
HGV-9 | Detection | Landmark extraction | 5 | Om | feature/landmark-extraction | In Progress
HGV-10 | Detection | FPS optimization | 8 | Adarsh Singh | feature/performance-optimization | To Do
HGV-11 | Gesture | Cursor mapping | 8 | Shivam Dhar Dubey | feature/cursor-mapping | In Progress
HGV-12 | Gesture | Pinch click | 5 | Vaibhav Kumar | feature/pinch-click | To Do
HGV-13 | Gesture | Gesture calibration | 3 | Sumit Kumar | feature/gesture-calibration | To Do
HGV-14 | Mouse | PyAutoGUI integration | 5 | Om | feature/pyautogui-integration | In Progress
HGV-15 | Mouse | Click execution | 3 | Danish Khan | feature/click-execution | To Do
HGV-16 | Deploy | Production config | 5 | Adarsh Singh | release/production-config | To Do
HGV-17 | Deploy | Render deployment | 5 | Gaurav Patel | release/render-deploy | To Do
HGV-18 | Deploy | Render fixes | 3 | Mihir Gupta | hotfix/render-issues | To Do
HGV-19 | UI | Simple UI | 5 | Siya Gangwar | feature/ui-design | In Progress
HGV-20 | UI | FPS display | 3 | Sumit Kumar | feature/fps-display | To Do
HGV-21 | UI | Latency optimization | 8 | Adarsh Singh | feature/latency-optimization | To Do
HGV-22 | Enhancement | Right click | 5 | Vaibhav Kumar | feature/right-click | Backlog
HGV-23 | Enhancement | Scroll gesture | 8 | Om | feature/scroll-gesture | Backlog
HGV-24 | Enhancement | Multi hand support | 13 | Mihir Gupta | feature/multi-hand-support | Backlog
HGV-25 | Enhancement | Gesture customization | 8 | Janhsi Gupta | feature/gesture-customization | Backlog
139